## City
IL - Wheaton - PD - IDOT | Status | Secondary Status | Permitting | Property Type | Validation Date | Device Type | Notes | 9 Falcons
#18- (WB) Butterfield @ W Loop | Installing | Sent for Scheduling | IL | DOT |  | Falcon | Rec'd IDOT permit approval 12/27 Sent to Field Team to schedule surveys and installations Pending a delayed order of specialized poles and bases (required by IDOT) in order to schedule all remaining installations in Illinois Pole instalaltions est. March '24
#14 (EB) Roosevelt @ Naperville- | Installing | Sent for Scheduling | IL | DOT |  | Falcon
#17 (EB) Roosevelt @ Country Farm - | Installing | Sent for Scheduling | IL | DOT |  | Falcon
#12- (EB) Roosvelt @ Lorraine | Installing | Sent for Scheduling | IL | DOT |  | Falcon
#13- (WB) Roosevelt @ Main | Installing | Sent for Scheduling | IL | DOT |  | Falcon
#15- (WB) Butterfield @ S Lambert | Installing | Sent for Scheduling | IL | DOT |  | Falcon
#10- (WB) Roosevelt @ Loraine | Installing | Sent for Scheduling | IL | DOT |  | Falcon
#16- (EB) Butterfield @ East Loop | Installing | Sent for Scheduling | IL | DOT |  | Falcon
#20 (EB) 56 @ Scottdale | Installing | Sent for Scheduling | IL | DOT |  | Falcon
IL - Wheaton - PD - County | Status | Secondary Status | Permitting | Property Type | Validation Date | Device Type | Notes | 8 Falcons
#09- (WB) Geneva @ Bloomingdale | Permitting | Submitted | Dupage, IL | County |  | Falcon | New location submitted to Dupage County on 11/16 Had to shift due to underground utilities
#03- SB County Farm @ The Tracks | In Service |  | DuPage County, IL | County |  | Falcon
#07- EB Geneva from Gary | In Service |  | DuPage County, IL | County | 2023-11-04 | Falcon
#05- (SB) Gary @ Geneva | In Service |  | DuPage County, IL | County |  | Falcon
#04- (EB) E Geneva @ N Main St | In Service |  | Dupage, IL | County | 2023-11-04 | Falcon
#02- (WB) Geneva @ Schmale | In Service |  | Dupage, IL | County | 2023-11-05 | Falcon
#19- (NB) Naperville @ Butterfield | In Service |  | Dupage, IL | County | 2023-08-24 | Falcon
#08- (SB) Naperville @ 56 | In Service |  | Dupage, IL | County | 2023-08-24 | Falcon
Wheaton - PD - City | Status | Secondary Status | Permitting | Property Type | Validation Date | Device Type | Notes | 3 Falcons
#11 WB 22nd @ Prospect Ct | In Service |  | Wheaton , IL | City | 2023-07-15 | Falcon
#06- (SB) President @ Geneva | In Service |  | Wheaton, IL | City | 2023-07-09 | Falcon
#01 S/B Main at Geneva | In Service |  | Wheaton, IL | City | 2023-07-08 | Falcon
Deployment Plans
IL - Wheaton - PD - IDOT
IL - Wheaton - PD - County
*Any site survey/installation dates listed above are tentative and subject to change
Updated: 2/12/2024

## AG Grant
IL - Wheaton - Grant 2023 | Status | Secondary Status | Permitting | Property Type | Validation Date | Device Type | Notes
#21 NB West @ Evergreen | Permitting | Submitted | Wheaton, IL | City |  | Falcon | Permit submitted to the City of Wheaton 1/10
#22 WB Roosevelt @ Fapp | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#23 NB Fapp Circle @ Roosevelt | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#30 WB E. Loop @ Sterling | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#31 EB E. Loop @ Naperville | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#32 SB S. Blanchard @ Naperville | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#34 SB Wheaton @ Front | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#35 NB Wheaton @ Front | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#36 NB Willow @ Cross | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#37 EB Willow @ Main | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#38 NB Main from Cole | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#39 NB Main @ Rotary Park | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#40 SB Main @ Indiana | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#42 NB W. Loop approaching Butterfield | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#43 NB President @ Railroad Tracks | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#44 WB College @ Stoddard | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#45 WB Roosevelt @ Delles | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#46 EB Front @ Ellis | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#48 SB Main @ Union | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#49 NB Main @ Harrison | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#50 SB Main @ Prairie | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#51 SB Blanchard @ Taft | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#54 EB Roosevelt @ Greenwood | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#57 EB Front @ Washington | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#59 SB Naperville @ Indiana | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#60 NB President @ Roosevelt | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#61 NB Carlton @ Roosevelt | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#62 SB Cross @ Liberty | Permitting | Submitted | Wheaton, IL | City |  | Falcon
#29 NB E. Loop @ Butterfield | Permitting | Submitted | Wheaton (City of), IL | City |  | Falcon
#55 NB Gary @ Royal Ct | Permitting | Research | N/A, IL | City |  | Falcon | Pending permit submittal to the City of Wheaton or MIlton Township Pending permitting team to clarify and submit
#24 SB County Farm @ Fapp Circle | Permitting | Submitted | DuPage County, IL | County |  | Falcon | Permit submitted to DuPage County 1/10
#26 NB South County @ Manchester | Permitting | Submitted | DuPage County, IL | County |  | Falcon
#52 SB Naperville @ Danada | Permitting | Submitted | DuPage County, IL | County |  | Falcon
#53 NB Naperville @ Danada | Permitting | Submitted | DuPage County, IL | County |  | Falcon
#27 NB Leask @ Butterfield | Installing | Sent for Scheduling | Milton Township, IL | Other |  | Falcon | Rec'd approved permits from MIlton Township Pending Field Team to schedule installations
#28 NB Leask @ Butterfield | Installing | Sent for Scheduling | Milton Township, IL | Other |  | Falcon
#25 SB Warrenville @ Roosevelt | Planning | Waiting on 3rd Party | Saburi Investment Group, IL | Private property |  | Falcon | Pending permission to install from property owner
#41 SB W. Loop approaching Butterfield | Planning | Awaiting Customer Approval | Wheaton, IL | City |  | Falcon | Pending PD to confirm they are OK with new locations before we move forward with permitting
#33 NB Blanchard @ Naperville | Planning | Awaiting Customer Approval | Wheaton (City of), IL | City |  | Falcon
#47 WB Wesley @ Scott | Planning | Awaiting Customer Approval | Wheaton, IL | City |  | Falcon
#56 NB Schmale @ Geneva | Planning | Awaiting Customer Approval | DuPage County, IL | County |  | Falcon
#63 SB E. Loop approaching Butterfield | Planning | Awaiting Customer Approval | Wheaton (City of), IL | City |  | Falcon
#64 NB Naperville @ Indiana | Planning | Awaiting Customer Approval | Wheaton (City of), IL | City |  | Falcon
#58 SB President @ Taft | Planning | Awaiting Customer Approval | Wheaton, IL | City |  | Falcon
Deployment Plan
IL - Wheaton - Grant 2023
*Any site survey/installation dates listed above are tentative and subject to change
Updated: 2/12/2024
44 total Falcons